IRCTC Website Redesign

End-to-End Implementation Plan

Scope: entire site (train search, results, booking, account, payments)

Prepared 18 August 2026

# 1. Executive Summary

This plan lays out a phased redesign of the IRCTC website — covering IA, visual design, the train search and booking flow, performance/reliability, and rollout strategy. IRCTC is a high-traffic, mission-critical government platform (peak load in the tens of thousands of bookings per minute during Tatkal windows), so the plan treats reliability and incremental rollout as first-class constraints, not afterthoughts bolted onto a visual refresh.

The redesign is scoped in four tracks that can run partly in parallel: (1) UX/IA and visual design system, (2) frontend rebuild, (3) backend/performance hardening for peak load, and (4) phased rollout with A/B validation. Recommended total timeline: 20–26 weeks to a full public rollout, with a usable beta available around week 10.

# 2. Current-State Pain Points (Research Findings)

Findings below are drawn from public UX critiques and aggregated user reviews of the live site, and should be validated with IRCTC's own analytics/support-ticket data before finalizing priorities.

Top recurring complaints - Search results show timings, coach types, fares and availability all at once with no hierarchy or filtering — users must scroll through long unordered lists to find a suitable train. - Little to no filtering (departure time window, train type, class) and results aren't sorted in an obviously useful order. - Frequent site outages and slowdowns during peak/Tatkal windows, especially around 10–11 AM booking windows. - Payment failures where money is debited but no ticket is issued, with slow or unclear refund resolution. - Session/login friction: OTP failures, forced logouts mid-booking, account lockouts. - Small tap targets and dense forms that don't follow platform conventions, increasing input errors.

Implication for the plan: a purely visual redesign will not fix the two complaints users mention most (reliability and payment/refund trust). Track 3 (backend/performance) and the payment-flow redesign in Track 2 are treated as equal priority to the visual refresh, not lower priority.

# 3. Goals & Non-Goals

## 3.1 Goals

- Cut time-to-first-usable-search-result and reduce cognitive load on the results page via filtering, sorting, and progressive disclosure.

- Redesign the booking and payment flow to eliminate ambiguous states (e.g., “money deducted, ticket unknown”) with clear status, retries, and reconciliation messaging.

- Establish a reusable design system (tokens, components) so future features ship faster and consistently.

- Meet WCAG 2.1 AA accessibility, given the platform's public-service, mass-market user base including low-literacy and older users.

- Make the site resilient at Tatkal-level peak concurrency without degrading the new UI's simplicity.

- Ship incrementally behind flags so the live booking system is never put at risk by the redesign.

## 3.2 Non-Goals (for this phase)

- Rebuilding the core PRS (Passenger Reservation System) / seat-inventory engine — out of scope; this plan treats it as an existing backend to integrate with.

- Native mobile app redesign — covered separately, though the shared design system should anticipate it.

- Loyalty program, catering (e-catering), and tourism package flows — addressed in a later phase once the core booking flow is stable.

# 4. Information Architecture

Reorganize around task-based navigation rather than department-based navigation (the current top nav mixes booking, PNR status, trains-between-stations, live tracking, and account settings with no clear hierarchy).

| Primary nav item | Contains | Notes |
| --- | --- | --- |
| Book a Train | Search, results, seat/coach selection, passenger details, payment | Primary task — default landing view |
| My Trips | Upcoming bookings, PNR status, live train status, cancellations, refund tracking | Consolidates 4 scattered current pages |
| Explore | Trains between stations, fare enquiry, seat availability calendar | Discovery/planning tools, separated from live booking |
| Help & Support | FAQs, refund status lookup, complaint tracking, contact | Surfaced prominently — currently buried |
| Account | Profile, saved passengers, payment methods, KYC/Aadhaar | Persistent icon, not a full nav item |

# 5. Train Search Page Redesign (Priority 1)

## 5.1 Search form

- Single-line, large-tap-target From/To fields with swap button, recent searches, and station autosuggest that tolerates partial/misspelled input.

- Inline date picker showing fare-class heatmap or at least a quota indicator (General/Tatkal) per day, so users don't pick a date blind.

- Persist last search + quota/class preference locally so repeat users (the majority, for daily commuters) skip re-entry.

## 5.2 Results list

- Default sort: departure time ascending, with an explicit sort control (duration, price, arrival time) — addresses the #1 cited complaint that results aren't in a sensible order.

- Filters as a persistent left rail on desktop / bottom sheet on mobile: departure time band, train type (Rajdhani/Shatabdi/Express/Passenger), class (SL/3A/2A/1A/CC), quota, and availability status only.

- Each result card shows only: train name/number, departure→arrival time with duration, and availability-by-class chips (color-coded: available/RAC/waitlisted). Fare and coach-composition detail moves to an expandable row — this directly answers the “too much simultaneous information” critique.

- Sticky mini search-summary bar at top so changing date/class doesn't require scrolling back up or re-searching.

## 5.3 Availability & fare detail (progressive disclosure)

- Tapping a class chip expands fare breakdown, boarding-point options, and a direct “Book” CTA inline, avoiding a full page navigation for a decision.

# 6. Booking & Payment Flow Redesign

This directly targets the reliability/trust complaints (deducted payments with no ticket, unclear refunds) that dominate current user reviews.

- Passenger details: shorter form, saved-passenger picker, inline validation (no full-page reload on error).

- Payment: single consolidated payment step with real-time status polling; never show a dead-end — every outcome (success, pending, failed) has an explicit next action.

- Ambiguous-state handling: if payment gateway confirms debit but booking confirmation is pending/unknown, show a persistent “Verifying” state with automatic reconciliation checks and a visible SLA (“we'll confirm within X minutes; if not, auto-refund is initiated”), rather than a silent failure.

- Post-booking: immediate ticket + PNR display, downloadable/shareable ticket, and one-tap add to “My Trips” with live status tracking.

- Refunds: a trackable refund-status timeline (not just a support ticket number) surfaced in My Trips.

# 7. Visual Design System

- Design tokens: color (with a distinct “Indian Railways” brand-appropriate palette), spacing scale, type scale, elevation — defined once, consumed everywhere.

- Component library: buttons, form inputs, date pickers, availability chips, cards, modals/bottom-sheets, toasts — built mobile-first since a majority of IRCTC traffic is mobile.

- Minimum 44×44px tap targets throughout (Fitts's-Law fix cited in current UX critiques).

- Support for Hindi + regional-language labels via a proper i18n layer, not hardcoded strings, matching IRCTC's actual multilingual user base.

- Dark-mode is a nice-to-have, not a priority — deprioritize versus reliability and clarity work.

# 8. Technical Approach

## 8.1 Frontend

- Component-driven rebuild (React or the team's existing stack) consuming the new design-system tokens/components as a shared package, so web and future mobile-web stay visually consistent.

- Server-side rendering or edge caching for the search/landing pages (mostly static/cacheable) to cut load time; the booking/payment steps remain dynamic and session-bound.

- Feature-flagged rollout so old and new UI can run side by side per user segment.

## 8.2 Backend & performance

- Load-test the redesigned search/results endpoints against realistic Tatkal-level concurrency before rollout; current outages are frequently tied to peak-window load, not just UI.

- Queueing/virtual-waiting-room pattern for Tatkal windows so the UI can show users an honest queue position instead of failing silently, if not already in place.

- Idempotent payment-confirmation handling with clear reconciliation jobs to eliminate the “debited but not booked” failure mode — this is a backend contract change the frontend redesign depends on.

## 8.3 Accessibility & QA

- WCAG 2.1 AA audit at each phase gate: color contrast, keyboard navigation, screen-reader labels on all form controls.

- Cross-device QA weighted toward low-end Android devices and slow (2G/3G) networks, reflecting real user conditions in Tier 2/3 cities.

# 9. Phased Implementation Plan

| Phase | Duration | Key deliverables |
| --- | --- | --- |
| 0. Discovery & baseline | 2 weeks | Analytics + support-ticket audit, current funnel drop-off analysis, stakeholder sign-off on scope |
| 1. IA & design system | 3–4 weeks | Sitemap, wireframes, token set, core component library, usability testing on prototypes |
| 2. Search & results rebuild | 4–5 weeks | New search form, filterable/sortable results page, shipped behind a feature flag to a small % of traffic |
| 3. Booking & payment rebuild | 5–6 weeks | New passenger/payment flow, reconciliation/refund-status UI, backend idempotency work in parallel |
| 4. Account / My Trips / support | 3 weeks | Consolidated My Trips, PNR/live status, help center restructure |
| 5. Hardening & load testing | 2–3 weeks | Peak-load simulation, accessibility audit, bug bash |
| 6. Phased public rollout | 3–4 weeks | Staged rollout by user %, monitor conversion/error rates, full cutover |

Total: approximately 22–27 weeks to full rollout, with a working beta (Phases 1–2) available for internal/limited-user testing around week 9–10.

# 10. Rollout Strategy & Risk Management

- Feature-flagged, percentage-based rollout: start at 1–5% of search traffic, expand gradually while watching booking-completion rate, error rate, and support-ticket volume as guardrail metrics.

- Instant rollback path: old UI stays live and routable until the new flow has proven itself across at least one full Tatkal cycle at scale.

- Never redesign booking/payment logic and UI in the same release: ship UI changes and backend reliability changes in separate, independently-verifiable releases so a regression can be isolated quickly.

- Peak-window freeze: no rollout changes during known high-traffic periods (festival travel seasons, long-weekend Tatkal windows).

- Communication: in-app changelog / “what's new” banner and an easy opt-back-to-old-UI link during the transition window, to reduce support load from confused repeat users.

# 11. Success Metrics

| Metric | Target direction |
| --- | --- |
| Search-to-booking conversion rate | ↑ increase |
| Median time from search to seat selection | ↓ decrease |
| Payment-ambiguous-state incidents (debited, no ticket) | ↓ decrease toward zero |
| Support tickets related to refunds/payment status | ↓ decrease |
| Site error rate / downtime during Tatkal windows | ↓ decrease |
| Task-success rate in usability testing (find & book a specific train) | ↑ increase |
| Accessibility audit pass rate (WCAG 2.1 AA) | 100% of core flows |

# 12. Immediate Next Steps

- Pull real analytics: funnel drop-off by step, top search-result abandonment points, and support-ticket categorization to replace assumption-based prioritization with data.

- Run 5–10 moderated usability sessions on the current site to validate/refine the pain points listed in Section 2.

- Stand up the design-token/component-library repo so Phase 1 has a foundation to build on from day one.

- Align with backend/platform team on the payment-idempotency and Tatkal-queueing work early, since it gates the Phase 3 UI.